## DDR Status
Status of Due Diligence Report for packages in remaining 70% sub-project IDIPT-T3
S. No. | Package No | Package Description | DPR No. | DPR Status | Components/ DPRs | Status as on 22- June - 2020 | DDR Approval from ADB | Pending at level | Issues Pending
1 | PB/IDIPT/T3/01/01 Lot-1 | State-wide Tourism Centers, Interpretation Centers (Lot 1)- Eastern Circuit at Ropar (Existing TIC) | 1 | prepared 21-10-16 | # TIC at Ropar | DDR submitted to ADB on 29-09-2016 | 13-10-2016
2 | PB/IDIPT/T3/01/01 Lot- 2 | State-wide Tourism Centers, Interpretation Centers (Lot 2)- Chandigarh, (Archieves Building, sector 38) | 2 | prepared soft copy of draft DDR for art work submitted on-10-03-16 | # TIC at Archives Bhawan, Chandigarh
3 | PB/IDIPT/T3/01/01 Lot-3 | State-wide Tourism Centers, Interpretation Centers (Lot 3)- Western Circuit at Kapurthala (Pushpa Gujral Science city) | 3 | prepared19-9-16 | # TIC & IC of Kanjali wetland at Pushpa Gujral Science City | DDR submitted to ADB on 9-09-2016 | 21-09-2016
4 | PB/IDIPT/T3/01/16 (lot-1) | State-wide Tourism Interpretation Signages in Eastern and Western Circuits | 4 |  | # Signages in Eastern and Western Circuit | DDR under revision by SSS-PMC for updation of list of sites. | 20-02-2020
5 | PB/IDIPT/T3/01/16 (lot-2) | State-wide Tourism Interpretation Signages in Eastern and Western Circuits | 5 |  | # New Media Designs
6 | PB/IDIPT/T3/02/17 Lot - 1 | State-level art and craft resource centers | 4 | prepared19-9-2016 | # Craft Resource Centres at Archives Bhawan, Chandigarh | DDR submitted to ADB on 09-11-2016 | 18-11-2016
7 | PB/IDIPT/T3/02/17 Lot - 2 | State-level art and craft resource centers | 5 |  | # Craft Resource Centres at Sangrur Kothi
8 | PB/IDIPT/T3/03-12/18 Lot- 1 | Imperial highway heritage conservation and visitor facility development (Lot 1) - Adaptive Reuse of Aam Khas Bagh and Interpretation centre/ Art & Craft centre at Maulsari | 6 | prepared19-9-2016 | # Maulsari - Interpretation centre, TIC, Craft Centre # Adaptive Reuse of Aam Khas Bagh # Conservation of remaining structures | DDR submitted to ADB on 09-12-2016 | 09-01-2017
9 | PB/IDIPT/T3/03-12/18 Lot - 2 | Imperial highway heritage conservation and visitor facility development (Lot 2)- Baradari and Kos Minars in Tarn Taran | 7 | prepared19-9-16 | # Conservation of Kos Minars # conservation of Baradari at Gandiwind | DDR submitted to ADB on 30.05.2018. Observations received from ADB to obtain NOC from school authorities for Baradari, compensation to land owners adjacent to Kos minars for loss of crops, preparation of RP as the subproject is assesed as catogory 'B' according to ADB's SBS, 2009. Compliance to the observations on DDR submitted to ADB on 27.08.18. Observations recieved from ADB on 26.09.18. DDR updated by reflecting documentry evidences that the work on Kos Minars will be undertaken during non-crop seasons, eligibility of recieving compensation in case of temporary impacts on land and crops. Revised DDR alongwith compliance matrix submitted to ADB on 10.12.18 | 2019-02-18 | PMC | DDR to be revised as per ADB's observations recieved on 28.09.18
10 | PB/IDIPT/T3/04/21 | Eco-tourism development at Ropar and Harike Wetlands (PICF) | 8 | prepared Dpr submitted on 07-09-2016. Instructions on the revision on comonents awaited from client deptt. | PIC (F) Works - Landscaping, Tree houses, Binoculars and telescopes, updation of existing amenities such as resting spots - Gazeebo and benches. | DDR sent to ADB on 18-01-2017. Package dropped | 01-02-2017 |  | Package dropped
11 | PB/IDIPT/T3/06/06 | Patiala Heritage Conservation and Tourism Development Project (Conservation of Shahi Samadhan, Heritage Walk and Darshani Deori at Patiala) | 11 | presentation ready. PMU to give date for presentation | # Development of Heritage Route- Conservation of Havelis facade improvement.Conservation of Shahi Samadhan, Heritage Walk and Darshani Deori at Patiala | DDR submitted to ADB on 29.08.2018. Updated DDR submitted to ADB on 03.06.2020. | 18-06-2020
12 | PB/IDIPT/T3/06/27 | Conservation of Mohindra Kothi | 13 | Preliminary concept report in progress | # Conservation of Mohindra Kothi and site development including parking/eco-cab parking | DDR submitted to ADB on 21.08.2018 | 2018-09-03
13 | PB/IDIPT/T3/06/31 | Adaptive reuse of Mohindra Kothi |  |  | # Adaptive reuse of Mohindra Kothi- Medal Gallery and Coin Gallery | DDR submitted to ADB on 13.11.2018 | 2018-11-16 |  | DDR Under Review by PMU
14 | PB/IDIPT/T3/07/08 Lot - 1 | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture (Lot 1) - Interpretation Centre at Chamkaur Sahib | 9 | prepared 19-9-16 | # Interiors works, Interpretation Centre, Interpretative Material, Chamkaur Sahib. | DDR submitted to ADB on 29-09-2016 | 13-10-2016
15 | PB/IDIPT/T3/07/08 Lot - 2 | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture (Lot 2) - Interpretation Centre at Wadda Ghallughara, Malerkotla | 10 |  | # Interpretation Centre Wadda Ghallughara, Malerkotla.
16 | PB/IDIPT/T3/07/08 Lot - 3 | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture (Lot 3) - Interpretation Centre at Chhota Ghallughara, Gurdaspur | 11 |  | # Interpretation Centre Chhota Ghallughara, Gurdaspur.
17 | PB/IDIPT/T3/07/08 Lot - 4 | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture (Lot 4) - Interpretation Centre at MRS Treaty site | 12 | prepared30-9-2016 | # Interpretation Centre and Development of Route along Satluj at MRS Treaty Signing site, Ropar. | DDR submitted to ADB on 29-09-2016 | 13-10-2016
18 | PB/IDIPT/T3/07/08 Lot - 5 | Establishment of Tourism facilities and Infrastructure Showcasing of Sikh culture (Lot-1)- New Technology based Multimedia works in Chamkaur Sahib |  |  | #New Technology based Multimedia works in Chamkaur Sahib | DDR submitted to ADB on 29-09-2016 | 13-10-2016
19 | PB/IDIPT/T3/08/10 | Remaining Conservation Works at Gobindgarh Fort - Amritsar | 19 | Worlk order for TSS issued to the TSS sub-consultant TSS is under progress | # Remaining Conservation Works | DDR submitted to ADB on 27.08.18 | 2018-09-05
20 | PB/IDIPT/T3/08/28 | Remaining landscapes work in Gobindgarh Fort - Amritsar | 20 |  | # Remaining Landscape Works | DDR submitted to ADB on 31.08.18 | 2018-09-05
21 | PB/IDIPT/T3/09/12 | Conservation of historic buildings along heritage walk in Amritsar - Qila Ahluwalia | 21 | Work order for TSS issued on dated 30-01-17 | # Development of Heritage Walk- Quila Ahluwalia | DDR submitted to ADB on 13.11.18. Observations recieved from ADB on DDR. Compliance to the query from ADB submitted on 21.01.19. | 2019-01-24 | PMC | DDR Under Review by PMU
22 | PB/IDIPT/T3/09/29 | Conservation and Adaptive reuse of Town Hall |  |  | # Adaptive re-use of Town Hall | DDR submitted to ADB on 18.10.18. | 2018-10-31 | PMC | DDR under preparation by SSS - PMC
23 | PB/IDIPT/T3/11/19 | Heritage conservation and tourism development in Gurdaspur district | 13 |  | # Provision of Parking and Toilets at Achaleshwar Dham, Batala # Conservation of Rattar Chhattar Mosque | DDR submitted to ADB on 20-06-2017. | 20-07-2017
24 | PB/IDIPT/T3/13/15 | Conservation and adaptive reuse of colonial heritage in Kapurthala – Gol Kothi, Gulabi Kothi and Buggy Khana | 16 | To be rebidded | # Conservation and Adaptive reuse of the Gol Kothi & Civil Rest House - Renovation, Landscaping, external lighting and visitors facilities. | Pending due to non possession of Gulabi Kothi from DG (Home guards) and Buggy Khana from DG Police Kapurthala. Draft DDR is ready. NoC from Distt. Administration and Medical Deptt awaited for Gulabi Kothi and Buggy Khana. DDR submitted to ADB for Gol Kothi on 27.02.19 | 2019-06-05 |  | Gulabi Kothi and Buggy Khana components dropped from the package.
25 | PB/IDIPT/T3/14/23 | Remaining conservation work at Aam Khas Bagh, Fatehgarh Sahib |  |  | Conservation and restoration of Hamam, Daulat Khana, Sard Khana, Water Channel and other restoration | DDR submitted to ADB on 11.05.2018 | 2018-05-31
26 | PB/IDIPT/T3/15/24 | Patiala Heritage Conservation work Qila Mubarak |  |  | Conservation of Moti Mahal at Qila Androon | DDR ssubmitted to ADB on 08.08.18 | 2018-09-03
27 | PB/IDIPT/T3/16/25 | Dedicated Footover Bridge to Gobidgarh Fort |  |  | Dedicated Footover Bridge to Gobidgarh Fort | Package dropped |  |  | Package dropped
28 | PB/IDIPT/T3/10/26 | Last mile connectivity to Keshopur Wetland |  |  | Last mile connectivity to Keshopur Wetland | DDR submitted to ADB on 18.10.18. | 2018-10-31 | DSC | DDR under preparation by SSS - DSC
29 | PB/IDIPT/T3/06/32 | Balance conservation works at Sheesh Mahal Patiala |  |  |  | DDR submitted to ADB on 09.01.19. Revised DDR submitted to ADB on 01.02.19 | 2019-05-16 | PMC | DDR to be prepared by SSS - PMC
30 | PB/IDIPT/T3/06/33 | Balance Conservation works at Ranbaas, Qila Mubarak, Patiala |  |  |  | DDR submitted to ADB on 29.11.18 | 2019-02-13 | PMC | DDR under preparation by SSS - PMC
31 | PB/IDIPT/T3/06/34 | Conservation works at Darbar Hall Qila Mubarak, Patiala |  |  | # Interior Upgradation of the Existing Museum setup in Darbar Hall. Art Conservation of Khatambandhi Ceiling, Decorative Ceiling. Doors and windows and Crystal Chandeliers. Setting Up Visitor Facilities like Cafeteria & Souvenir Shop in the Extension Block between Darbar Hall & Main Gate Structures. Providing Signage & Visitor Movement and Digital Information mediums for a better Visitor Experience. | DDR submitted to ADB on 19.12.18 | 2019-02-13 | PMC | DDR to be prepared by SSS - PMC
32 | PB/IDIPT/T3/13/36 | Conservation of remaining building Darbar Hall, Kapurthala |  |  |  | DDR submitted to ADB on 06.12.18. As suggested by ADB resubmitted DDR after incorporating the NoC from PWD and countersigned by D.C, Kapurthala on 11.02.19. Comments received on revised DDR on 12.02.19 to provide compliance to usage of parking area as storage by the contactor and impact on lawyer’s chambers. Compliance to the comments submitted on 07.03.19. Revised DDR submitted to ADB on 15.05.19 | 2019-05-23 | PMC | DDR to be prepared by SSS - PMC
33 | PB/IDIPT/T3/09/37 | Improvement of façade of building along the approach road to Durgiana Temple, Amritsar |  |  |  | XEN, Municipal Corporation, Amritsar vide letter no. XEN-I (C)/364 dt 05.11.18 has intimated that Municipal Corporation, Amritsar will execute the façade work at Durgiana Temple. |  | PMC | DDR to be prepared by SSS - PMC
34 | PB/IDIPT/T3/09/38 | Beautification works near Gurudwara Baba Deep Singh ji at Amritsar |  |  |  | Site plan/ Layout map along with photographs of the project site submitted to ADB on 30.04.19. RP and DDR prepared. DDR submitted to ADB on 06.06.19. RP submitted to ADB 07.08.19 | 2019-08-12
35 | PB/IDIPT/T3/09/39 (lot-1) | Facade improvement works on 3 Heritage walk streets in Amritsar- Hall Bazar and Katra Jaimal (lot-1) |  |  | # Developing façade of 147 no. of buildings along Hall Bazar Street and developing façade of 133 no. of buildings along Katra Jaimal Street for unification through colours, materials, enhancing shop fronts, vibrant signage and street lighting to define the street character and defining building lines. | DDR submitted to ADB on 13.11.18 | 2018-11-15 | PMC | DDR to be prepared by SSS - PMC
36 | PB/IDIPT/T3/09/39 (lot-2) | Facade improvement works on 3 Heritage walk streets in Amritsar-Ramsar and Katra Ahluwalia (lot-2) |  |  | # Developing façade of 114 no. of buildings along Ramsar Street (650 m) and developing façade of 162 no. of buildings along Katra Ahluwalia Street (500 m) for unification through colours, materials, enhancing shop fronts, vibrant signage and street lighting to define the street character and defining building lines. | DDR submitted to ADB on 13.11.18 | 2018-11-15
37 | PB/IDIPT/T3/06/40 | Conservation works of Diwan Khana (Balance works), Marble Baradari and Clock Tower at Sangrur |  |  | Package dropped | DDR submitted by SSS-PMC on 03.05.19. Reviewed by ESS-PMU. Submitted to competent authority for further perusal on 09.05.19. DDR submitted to ADB on 16.05.19. | 2019-05-30
38 | PB/IDIPT/T3/06/41 | Development of Banasar bagh and Baradari Tank at Sangrur |  |  | Package dropped | DDR submitted to ADB on 11.05.19. NoC awaited from D.C, Sangrur for Banasar Bagh. | 2019-08-28
39 | PB/IDIPT/T3/06/42 | Development works at village Ghuram, Patiala as heritage village and linking it to the tourist circuit |  |  | Package dropped | DDR prepared. Submission due to ADB. Non-receipt of NoC from Director, Culture for Ghuram.
40 | PB/IDIPT/T3/06/43 | Conservation work of Moonak Fort, District Sangrur |  |  | Package dropped | DDR submiitted to ADB on 13.06.19. Revised DDR submitted to ADB on 27.08.19
41 | PB/IDIPT/T3/16/44 | Renovation of Memorial of Former President of India Late Gyani Zail Singh Ji at Faridkot |  |  | Package dropped | DDR prepared and submitted to the competent authority for approval
42 | PB/IDIPT/T3/06/45 | Construction of Shaheed Udham Singh Memorial at Sunam, District Sangrur |  |  | Package dropped | Draft DDR prepared.Submission due to ADB.
Legend
Approved packages by ADB
Packages under preparation
Dropped Packages