## IEE Status
IEE Status for Packages in Remaining 70 % Subproject- IDIPT- T3
S. No. | Package No | Package Description | Components/ DPRs | IEE Report Status as on 21.06.2020 | IEE uploaded on ADB Website
1 | PB/IDIPT/T3/01/01 Lot 1 | State-wide Tourism Centers, Interpretation Center- Eastern Circuit at Ropar (Existing TIC) (Lot 1) | # TIC at Ropar | IEE report submitted to ADB on 20.04.17. Approved by ADB on 11.05.2017 | Yes
2 | PB/IDIPT/T3/01/01 Lot 2 | State-wide Tourism Centers, Interpretation Center- Eastern Circuit -TIC at Archives Bhawan, Sector 38, Chandigarh (Lot 2) | # TIC at Archives Bhawan, Chandigarh
3 | PB/IDIPT/T3/01/01 Lot 3 | State-wide Tourism Centers, Interpretation Centers (Lot 3)- Western Circuit at Kapurthala (Pushpa Gujral Science city) | # TIC & IC of Kanjali wetland at Pushpa Gujral Science City. | IEE report submitted to ADB on 09.11.16, Comments received from ADB on 15.11.16. Report revised as per ADB's observation. Revised IEE report along with compliance matrix submitted to ADB on 09.12.16. Approved by ADB on 13.01.2017 | Yes
4 | PB/IDIPT/T3/02/17-Lot 1 | State-level art and craft resource center at Archives Bhawan, Chandigarh (Lot 1) | # Craft Resource Centres at Archives Bhawan, Chandigarh. | IEE report submitted to ADB on 20.10.16. Approved by ADB on 20.10.2016 | Yes
5 | PB/IDIPT/T3/02/17-Lot 2 | State-level art and Craft Resource Centre at Sangrur Kothi (Lot 2) | # Craft Resource Centres at Sangrur Kothi
6 | PB/IDIPT/T3/03-12/18-Lot 1 | Imperial highway heritage conservation and visitor facility development (Lot 1) - Adaptive Reuse of Aam Khas Bagh and Interpretation centre/ Art & Craft centre at Maulsari | # Maulsari - Interpretation centre, TIC, Craft Centre # Adaptive Reuse of Aam Khas Bagh # Conservation of remaining structures | IEE report submitted to ADB on 23.12.16. Comments received from ADB on 06.01.17. Report revised as per ADB's observation. IEE report along with compliance matrix submitted to ADB on 18.01.17. Approved by ADB on 27.01.2017. IEE report revised due to additional scope of work (site development and landscaping of inner court and around the building) and submitted to ADB on 07.03.19 and approved by ADB on 02.04.19. | Yes
7 | PB/IDIPT/T3/03-12/18-Lot 2 | Imperial highway heritage conservation and visitor facility development (Lot 2)- Baradari and Kos Minars in Tarn Taran | # Conservation of Kos Minars # conservation of Baradari at Gandiwind | IEE submitted to ADB on 23.05.17. Observations recieved from ADB on 30.05.17. Individual NOCs for State protected Kos minars-Gahri and Cheema obtined from DCAM. Revised IEE Submitted to ADB on 30.04.18. Approved by ADB on 09.05.2018 | Yes
8 | PB/IDIPT/T3/04/21 | Eco-tourism development at Ropar and Harike Wetlands (PICF) | PIC (F) Works - Landscaping, Tree houses, Binoculars and telescopes, updation of existing amenities such as resting spots - Gazeebo and benches. | Package dropped.
9 | PB/IDIPT/T3/07/08 (Lot1) | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture- Interpretation Centre at-Chamkaur Sahib (Lot 1) | # Interiors works, Interpretation Centre, Interpretative Material, Chamkaur Sahib. | IEE report submitted to ADB on 20.10.16. Approved by ADB on 22.11.2016 | Yes
10 | PB/IDIPT/T3/07/08 (Lot 2) | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture- Interpretation Centre at-Centre Wadda Ghallughara, Malerkotla (Lot 2) | # Interpretation Centre Wadda Ghallughara, Malerkotla.
11 | PB/IDIPT/T3/07/08 (Lot 3) | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture- Interpretation Centre at- Chhota Ghallughara, Gurdaspur (Lot 3) | # Interpretation Centre Chhota Ghallughara, Gurdaspur.
12 | PB/IDIPT/T3/07/08 (Lot 5) | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture- New Technology based multimedia works in Chamkaur Sahib (Lot 5) | # New Technology based multimedia works in Chamkaur Sahib
13 | PB/IDIPT/T3/07/08 (Lot 4) | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture (Lot 4) - Interpretation Centre at MRS Treaty site | # Interpretation Centre and Development of Route along Satluj at MRS Treaty Signing site, Ropar. | IEE report submitted to ADB on 13.10.16. Approved by ADB on 20.10.2016 | Yes
14 | PB/IDIPT/T3/11/19 | Heritage conservation and tourism development in Gurdaspur district |  | IEE report submitted to ADB on 08.05.17. Approved by ADB on 01.06.17. IEE re-submitted to ADB on 30.04.18 due to revision in scope of works. IEE report approved by ADB on 09.05.18 | Yes
15 | PB/IDIPT/T3/13/15 | Conservation and adaptive reuse of colonial heritage in Kapurthala – Gol Kothi, Gulabi Kothi and Buggy Khana | # Conservation and Reuse of Buggy Khana # Conservation and Restoration of Gulabi Kothi # Conservation and Adaptive reuse of the Gol Kothi & Civil Rest House - Renovation, Landscaping, external lighting and visitors facilities. | IEE report submitted to ADB on 08.11.16, Comments received from ADB on 15.11.16. Revised IEE report along with compliance matrix submitted to ADB on 09.12.16. IEE Report Approved by ADB on 13.04.17. Work in progress only at Gol Kothi due to no-vaccation of Gulabi Kothi (Punjab Home-guards) and Buggy Khana (Punjab Police) | Yes
16 | PB/IDIPT/T3/06/06 | Patiala Heritage Conservation and Tourism Development Project (Conservation of Shahi Samadhan, Heritage Walk and Darshani Deori at Patiala | # Development of Heritage Route- Conservation of Havelis facade improvement.Conservation of Shahi Samadhan, Heritage Walk and Darshani Deori at Patiala | IEE submitted to ADB on 20.07.18. Due to droping of the component- development of Env Park and Parking at Sheesh Mahal IEE report was revised and submitted to ADB on 13.08.2018. IEE was re-submitted by udating scope on 24.09.18. IEE Report approved by ADB on 30.10.18. | Yes
17 | PB/IDIPT/T3/06/27 | Conservation of Mohindra Kothi, Patiala | # Conservation of Mohindra Kothi and site development including parking/eco-cab parking | IEE submitted to ADB on dated 09.07.2018. IEE report approved by ADB on 20.07.18. | Yes
18 | PB/IDIPT/T3/06/31 | Adaptive reuse of Mohindra Kothi, Patiala | # Adaptve reuse of Mohindra Kothi as Coin gallery and Medal gallery | IEE submitted to ADB on 16.07.2019. IEE Report approved by ADB on 29.07.19. | Yes
19 | PB/IDIPT/T3/08/10 | Remaining Conservation Works at Gobindgarh Fort - Amritsar | # Remaining Conservation Works | IEE report submitted to ADB on 25.07.18. Approved by ADB on 31.07.2018. | Yes
20 | PB/IDIPT/T3/08/28 | Remaining landscapes work in Gobindgarh Fort - Amritsar | # Remaining Landscape Works | IEE submitted to ADB on 07.08.2018. IEE Report Approved by ADB on 05.09.18. | Yes
21 | PB/IDIPT/T3/09/12 | Conservation of historic buildings along heritage walk in Amritsar - Qila Ahluwalia | # Development of Heritage Walk- Qila Ahluwalia | IEE submitted to ADB on 11.10.2018. IEE Report Approved by ADB on 30.10.18. | Yes
22 | PB/IDIPT/T3/01/16 (Lot-1) | State-wide Tourism Interpretation Signages, Eastern and Western Circuit | # Signages in Eastern and Western Circuit | IEE submitted to ADB on 20.12.2019. IEE Report Approved by ADB on 23.12.19. | Yes
32 | PB/IDIPT/T3/01/16 (Lot-2) |  | # New Media Designs
24 | PB/IDIPT/T3/14/23 | Remaining conservation work at Aam khas bagh Fatehgarh Sahib | Conservation and restoration of Hamam, Daulat Khana, Sard Khana, Water Channel and other restoration | IEE submitted to ADB on 13.06.2018. Observations from ADB received on 19.06.2018 to incorporate details about the approach road (200 m length) from Aam Khas Bagh to Main road. IEE revised and compliance matrix submitted to ADB on 31.08.18. Approved by ADB on 14.09.18. | Yes
25 | PB/IDIPT/T3/15/24 | Patiala Heritage Conservation work Qila Mubarak | Conservation and restoration of Moti Mahal at Qila Androon, Qila Mubarak | IEE submitted to ADB 15.06.2018. ADB approved IEE on 04.07.2018. | Yes
26 | PB/IDIPT/T3/16/25 | Dedicated Footover Bridge to Gobindgarh Fort | Dedicated Footover Bridge to Gobindgarh Fort | Package dropped.
27 | PB/IDIPT/T3/10/26 | Last mile connectivity to Keshopur Wetland, Gurdaspur district | Last mile connectivity to Keshopur Wetland | IEE submitted to ADB on 15.05.18. ADB's observation received on 20.06.2018 to incorporate location maps showing project road and KCCR wetland, technical inputs related to approach road and proposed impacts if any, proposed due to upgrading and strenghtening of road. Revised IEE report submitted to ADB alongwith revised compliance matrix on 10.10.18. ADB approved IEE report on 11.10.2018. | Yes
28 | PB/IDIPT/T3/09/29 | Conservation and Adaptive reuse of Town Hall | Adaptive reuse of Town Hall | IEE report submitted to ADB on 08.10.18. Revised IEE submitted to ADB on 06.12.18. ADB approved IEE report on 07.12.2018. | Yes
29 | PB/IDIPT/T3/06/32 | Balance conservation works at Sheesh Mahal Patiala | #Museum upgradation, design of galleries and period rooms. Restoration of historic interiors Site interpretation and visitor facilities | IEE report submitted to ADB on 29.10.18. ADB approved IEE on 15.11.2018. | Yes
|  | Revised name: Facade lighting of Sheesh Mahal and other buildings | Revised scope: # Facade lighting and Solar PV panel installation of Sheesh Mahal in Patiala. Facade and landscape lighting, Solar PV panel installation of Mohindra Kothi in Patiala. Facade and landscape lighting & Solar PV panel installation of Sangrur Kothi. Facade, landscape and interior lighting & Solar PV panel installation of Gol Kothi in Kapurthala. | IEE report submitted to ADB on 11.12.19. ADB approved IEE on 03.03.2020. | Yes
30 | PB/IDIPT/T3/06/33 | Balance Conservation works at Ranbaas, Qila Mubarak, Patiala | #Conservation & Restoration of the External Façade; Interior Restoration of the Historic materials; Adaptive Reuse & Up-gradation of Ranbas as a Heritage Boutique Stay. Conservation & protection of Rang Mahal and Sheesh Mahal including their interiors and decorative wall surface; Setting up Visitor facilities like Cafeteria and Souvenir Shop. | IEE report submitted to ADB on 18.10.2018. ADB approved IEE on 30.10.2018. | Yes
31 | PB/IDIPT/T3/06/34 | Conservation works at Darbar Hall Qila Mubarak, Patiala | # Interior Upgradation of the Existing Museum setup in Darbar Hall. Art Conservation of Khatambandhi Ceiling, Decorative Ceiling. Doors and windows and Crystal Chandeliers. Setting Up Visitor Facilities like Cafeteria & Souvenir Shop in the Extension Block between Darbar Hall & Main Gate Structures. Providing Signage & Visitor Movement and Digital Information mediums. | IEE report submitted to ADB 18.10.2018. ADB approved IEE on 30.10.2018. | Yes
|  | Revised name: Facade Lighting of Darbar Hall and adjoining buildings at Qila Mubarak, Patiala | Revised scope: # Facade lighting of Darbar Hall, Facade lighting of Ranbass,Facade lighting of Entrance gate of Qila Androon, Facade lighting of Entrance gate of Qila Mubarak from inside only, Lighting of courtyard in Qila Mubarak, and Installation of solar PV panels. | IEE report submitted to ADB on 09.12.19. ADB approved IEE on 10.12.2019. | Yes
32 | PB/IDIPT/T3/13/36 | Conservation of remaining building Darbar Hall, Kapurthala | # Adaptive reuse of Darbar Hall and 2 adjacent blocks as 15 room Hotel. Conservation and Restoration of 2 adjacent blocks. Upgradation and completion of interior parts like plaster works, flooring works, doors and windows, ceiling works. Improvement of all the toilets and the related plumbing works. Upgradation and installation of electrical works like internal lights, decorative lights, emergency lights, Installation of signages and interpretation boards. | Revised IEE submitted to ADB on 06.12.18. ADB approved IEE on 14.12.2018. | Yes
33 | PB/IDIPT/T3/09/37 | Improvement of façade of building along the approach road to Durgiana Temple, Amritsar |  | XEN, Municipal Corporation, Amritsar vide letter no. XEN-I (C)/364 dt 05.11.18 has intimated that Municipal Corporation, Amritsar will execute the façade work at Durgiana Temple.
34 | PB/IDIPT/T3/09/38 | Beautification works near Gurudwara Baba Deep Singh ji at Amritsar | Façade improvement and conservation throughout the stretch from Khazana Chowk to Sultanwind Chowk (3.3 Km) | IEE submitted to ADB on 25.03.19. NoC from shopkeepers awaited. ADB approoved IEE on 02.04.19. | Yes
35 | PB/IDIPT/T3/09/39 (lot-1) | Facade improvement works on 3 Heritage walk streets in Amritsar- Hall Bazar and Katra Jaimal (lot-1) | # Developing façade of 147 no. of buildings along Hall Bazar Street and developing façade of 133 no. of buildings along Katra Jaimal Street for unification through colours, materials, enhancing shop fronts, vibrant signage and street lighting to define the street character and defining building lines. | IEE report submitted to ADB on 27.11.18. Revised IEE submitted on 17.12.18. ADB approoved IEE on 18.12.18. | Yes
36 | PB/IDIPT/T3/09/39 (lot-2) | Facade improvement works on 3 Heritage walk streets in Amritsar-Ramsar and Katra Ahluwalia (lot-2) | # Developing façade of 114 no. of buildings along Ramsar Street (650 m) and developing façade of 162 no. of buildings along Katra Ahluwalia Street (500 m) for unification through colours, materials, enhancing shop fronts, vibrant signage and street lighting to define the street character and defining building lines. | IEE submitted to ADB on 21.01.19. ADB appoved IEE on 29.01.19. | Yes
37 | PB/IDIPT/T3/06/40 | Conservation works of Diwan Khana (Balance works), Marble Baradari and Clock Tower at Sangrur | Package dropped. | IEE submitted to ADB on 30.05.19. ADB appoved IEE on 03.06.19 | Yes
38 | PB/IDIPT/T3/06/41 | Development of Banasar bagh and Baradari Tank at Sangrur | Package dropped. | NoC awaited from D.C, Sangrur for Banasar Bagh. IEE submitted to ADB on 06.06.2019.Observations from ADB received on 13.06.2019 to revise IEE by providing clarity on scope of works. IEE under updation.
39 | PB/IDIPT/T3/06/42 | Development works at village Ghuram, Patiala as heritage village and linking it to the tourist circuit | Package dropped. | IEE report submitted to ADB on 12.04.19. Observations from ADB received on 24.04.2019 to revise IEE by providing details of Bir Bhunerheri WLS to project site with the help of a map and change in scope of work 'jungle clearance' to removal of shrubs and bushes. Revised IEE submitted to ADB on 09.05.19. ADB appoved IEE on 16.05.19. NoC awaited from Director, Culture. | Yes
40 | PB/IDIPT/T3/06/43 | Conservation work of Moonak Fort, District Sangrur | Package dropped. | IEE report submitted to ADB on 26.04.2019. ADB appoved IEE on 06.05.19. | Yes
41 | PB/IDIPT/T3/16/44 | Renovation of Memorial of Late Dr. Giani Zail Singh (Former President of India) at existing jail in Faridkot. | Package dropped. | IEE submitted to ADB on 19.06.2019. | Yes
42 | PB/IDIPT/T3/06/45 | Construction of Memorial of Shaheed Udham Singh Ji at Sunam, Sangrur. | Package dropped. | IEE submitted to ADB on 10.07.2019.
Legend
Approved packages by ADB
Packages under preparation
Dropped Packages

## Sheet1 (hidden)
Status for 10 No. Priority Packages in Remaining 70 % Subproject- IDIPT T3
S. No. | Consultant | Package No | Package Description | DPR No. | Components/ DPRs | Estimated value in INR CR | Nature of work | Concept presentation | Concept report | SAR Cost INR Cr | Prepared DPR Cost INR CR | Date of receiving of Soft copy of Draft DPR | Date of receiving of Soft copy of final DPR | Date of Final DPR in Hard Copy | IEE Report Status | Status as on 26.09.2016
1 | GMK | PB/IDIPT/T3/01/01 Lot1 | State-wide Tourism Centers, Interpretation Centers (Lot 1)- Eastern Circuit at Ropar (Existing TIC), and Chandigarh, (Archieves Building, sector 38) | 1 | # TIC at Ropar | 6 | Civil | 2016-05-10 | 2016-05-18 | 1 | 0.33 | 2016-06-14 | 2016-09-05 |  | ESS-DSC submitted IEE report to PMC. Report under review by ESS-PMC | Soft copy of Final DPR recieved, under review
|  |  |  | 2 | # TIC at Archives Bhawan, Chandigarh |  |  | 2016-05-27 | 2016-08-11 | 2 | 2.84 | 2016-09-05 |  |  |  | Draft DPR submitted, Shortcomings in the BOQ to be discussed with GMK
2 | GMK | PB/IDIPT/T3/01/01 Lot 2 | State-wide Tourism Centers, Interpretation Centers (Lot 2)- Western Circuit at Kapurthala (Pushpa Gujral Science city) | 3 | # TIC & IC of Kanjali wetland at Pushpa Gujral Science City |  | Civil | 2016-06-27 | 2016-08-03 | 2.5 | 2.33 | 2016-09-17 |  |  | ESS-DSC submitted IEE report to PMC. Report under review by ESS-PMC | Draft DPR submitted, under review.
3 | SHP | PB/IDIPT/T3/01/16 | State-wide Tourism Signages (Lot 1), Eastern Circuit | 4 | #Signages in Eastern Circuit; | 5.64 | Civil | [8 empty] | To be addressed by SHP
4 | SHP | PB/IDIPT/T3/01/16 | State-wide Tourism Signages (Lot 2), Western Circuit | 5 | #Signages in Western Circuit; |  | Civil | [8 empty] | To be addressed by SHP
[5 empty] | Total Package cost | [5 empty] | 5.5
3 | San | PB/IDIPT/T3/02/17 | State-level art and craft resource centers | 4 | # Craft Resource Centres at Archives Bhawan, Chandigarh | 3.42 | Civil | 2016-04-29 | 2016-05-03 | 1.81 | 1.36 | 2016-06-06 | 2016-09-07 | Received | PMU Submitted IEE report to ADB on 06.09.16, Comments received telephonically from ADB. Report revised by ESS-PMU as per ADBs comments & suggestion. IEE report sent to Safeguard Specialist, ADB on 04.10.16. | Final DPR received, BoQ being modified in house by PMC for preparation of Bid Document.
|  |  |  | 5 | # Craft Resource Centres at Sangrur Kothi |  |  | 2016-04-29 | 2016-05-03 | 1.71 | 3.87 | 2016-06-06 | 2016-09-07 | Received |  | Final DPR received, BoQ being modified in house by PMC for preparation of Bid Document.
[5 empty] | Total Package cost | [5 empty] | 5.23
4 | CRCI | PB/IDIPT/T3/03-12/18 | Imperial highway heritage conservation and visitor facility development (Lot 3) - Adaptive Reuse of Aam Khas Bagh and Interpretation centre/ Art & Craft centre at Maulsari | 6 | # Maulsari - Interpretation centre, TIC, Craft Centre # Adaptive Reuse of Aam Khas Bagh # Conservation of remaining structures | 5.04 | Conservation | 2016-05-20 | 2016-05-23 | 2.61 | 3.5 | 2016-06-25 | 2016-09-12 |  | DSC submitted IEE report to PIU, Ropar on 26.09.16. Report under review. | Final DPR received but there are number of shortcomings in final DPR as use of lime mortar in Malsari Building. Proposal of interpretation Centre and Art and Craft Centre & TIC is missing. Comments sent to PMU
5 | CRCI | PB/IDIPT/T3/03-12/18 | Imperial highway heritage conservation and visitor facility development (Lot 4)- Baradari and Kos Minars in Tarn Taran | 7 | # Conservation of Kos Minars # conservation of Baradari at Gandiwind |  |  | 2016-05-20 | 2016-05-23 | 2.43 | 2.3 | 2016-06-25 | 2016-09-15 |  | PMU shared comments on IEE report with PMC on 12.09.16, PMC yet to revise the report. After receiving the updated IEE from PMC, it shall be finalised. | Ownership issue to be finalised by PM-PIU for Baradari.
[5 empty] | Total Package cost | [5 empty] | 5.8
6 | GMK | PB/IDIPT/T3/04/21 | Eco-tourism development at Ropar and Harike Wetlands (PICF) | 8 | PIC (F) Works - Landscaping, Tree houses, Binoculars and telescopes, updation of existing amenities such as resting spots - Gazeebo and benches. | 2.22 | Civil | 2016-07-13 | 2016-07-25 | 2.22 | 2.7 | 2016-09-02 |  |  | DSC submitted IEE report to PIU, Ropar on 26.09.16. Report under review. | Scope of work not finalised yet. Forest Department to give suggestions as discussed in the meeting held on 20-09-2016.
9 | GMK | PB/IDIPT/T3/06/06 | Patiala heritage conservation and tourism development project (Heritage Walk, Parking Areas, Mohindra Kothi) | 11 | # Development of Environmental Park and Parking, Sheesh Mahal. | 26.46 | Civil
|  |  |  | 12 | # Development of Heritage Route- Conservation of Havelis facade improvement, Eco-Cab parking facilities.
| San |  |  | 13 | # Conservation and Adaptive reuse of of Mohindra Kothi- Art & craft Centre, TIC, Medal Gallery and Guest House.
| CRCI |  |  | 14 | # Remaining Works of Nabha Fort. (8.37 cr) |  | Conservation
7 | San | PB/IDIPT/T3/07/08 | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture (Lot 1) - Interpretation Centres at Chamkaur Sahib, Wadda and Chhota Ghallughara | 9 | # Interiors works, Interpretation Centre, Interpretative Material, Chamkaur Sahib. | 18.12 | Civil | 2016-04-29 | 2016-05-03 | 13.01 | 13.24 | 2016-06-06 | 2016-09-07 | Received | PMU shared comments on IEE with PMC on 02.09.16, PMC/PMU revised the report. Report updated by ESS-PMU, IEE report Sent to Safeguard Specialist, ADB on 04.10.16. | Final DPR received, modified in house by PMC, ready for Tendering.
|  |  |  | 10 | # Interpretation Centre Wadda Ghallughara, Malerkotla. |  |  | 2016-04-29 | 2016-05-03 | 1.5 | 1.54 | 2016-06-06 | 2016-09-07 | Received
|  |  |  | 11 | # Interpretation Centre Chhota Ghallughara, Gurdaspur. |  |  | 2016-04-29 | 2016-05-03 | 1.5 | 1.57 | 2016-06-06 | 2016-09-07 | Received
8 | GMK | PB/IDIPT/T3/07/08 | Establishment of Tourism facilities and infrastructure showcasing of Sikh culture (Lot 2) - Interpretation Centre at MRS Treaty site | 12 | # Interpretation Centre and Development of Route along Satluj at MRS Treaty Signing site, Ropar. |  |  | 2016-05-27 | 2016-06-10 | 1.1 | 1.67 | 2016-06-09 | 2016-09-09 |  | PMU Submitted IEE report to ADB on 06.09.16, Comments recieved from ADB telephonically. Report revised by ESS-PMU as per ADB's comments & suggestion. IEE report sent to Safeguard Specialist, ADB on 03.10.16. | Soft copy of Final DPR received, modified in house by PMC, ready for Tendering.
12 | CRCI | PB/IDIPT/T3/08/10 | Adaptive reuse at Gobindgarh fort, Lot-3 | 19 | Anglo Sikh Museums (North East Bastion) (8 cr) # Exhibition Hall (Khas Mahal) (1 cr) # Ticketing for Museums/ Craft shops/Art and Craft Centre (Eastern/Northern Cells) (2.61 cr) # Administrative Offices, VIP Rest Room, Ticket Counter and Toilets (Detention Centre) # Sikh Regiment gallery (North West Bastion) (8 cr) # Auditorium Cum Conference Room (Badminton and Squash Court) # Interpretation of British Theme (Choloronome House) and Dining Hall/Kitchen/Toilets (Baracks) # Ticket check Point/Crafts Shops/Souvenir Shop (Nalwa Gate), Stable (Stable) (0.4 cr) # Centre for Peace, Reconcilation and the Arts. (South West Bastion) (8 cr) # Bio-diversity park/Multi cuisine Restaurant/Tented Accomodations (North Ravelin) # Childrens Adventure Park/Multi Cuisine Restaurant/Tented Accomodation (West Ravelin) # The rampart connecting north-east and north-west basins will have installations like weapons and artillery. while the rampart connecting north west and south-west basins will have installation on the partition (North and West Rampart) | 26.33 | Civil |  |  |  | 18.02 |  |  |  |  | To be commenced by concessionaire under PPP mode.
|  |  |  | 20 | # Remaining Conservation Works | 2 | Conservation | [8 empty] | Yet to get update from sub-consultant
13 | CRCI | PB/IDIPT/T3/09/12 | Conservation and adaptive reuse of town hall, Rambagh gate and historic buildings along heritage walk in Amritsar – Reuse at Town and Conservation Works at Heritage Walk | 21 | # Adaptive re-use of Town Hall | 15.96 | Civil
|  |  |  | 22 | # Conservation, Restoration / Improvement of Rambagh Gate |  | Conservation
| San |  |  | 23 | # Development of Heritage Walk- Quila Ahluwalia and Shani Temple | [10 empty] | Yet to get update from sub-consultant
[5 empty] | Total Package cost | [5 empty] | 18.02
9 | GMK | PB/IDIPT/T3/11/19 | Heritage conservation and tourism development in Gurdaspur district | 13 | # Provision of Parking and Toilets, Achaleshwar Dham, Batala | 3 | Civil | 2016-05-10 | 2016-05-18 | 0.8 | 0.9 | 2016-06-14 | 2016-09-03 |  | PMU shared comments on IEE with PMC on 06.09.16, PMC yet to revise the report. After receiving the updated IEE from PMC, it shall be finalised. | NOC from Waqaf board is pending.
| CRCI |  |  | 14 | # Conservation of Panj Mandir, Fatehgarh Churiyan |  | Conservation | 2016-05-20 | 2016-05-23 | 1 | 1 | 2016-06-25 | 2016-08-12
|  |  |  | 15 | # Conservation of Rattar Chhattar Mosque |  |  | 2016-05-20 | 2016-05-23 | 1.2 | 1.77 | 2016-06-25
[5 empty] | Total Package cost | [5 empty] | 3.67
10 | CRCI | PB/IDIPT/T3/13/15 | Conservation and adaptive reuse of colonial heritage in Kapurthala – Gol Kothi, Gulabi Kothi and Buggy Khana | 16 | # Conservation and Reuse of Buggey Khana | 10.86 |  | 2016-05-20 | 2016-05-23 | 4 | 7.68 | 2016-06-25 |  |  | PMU shared comments on IEE report with PMC on 23.09.16, PMC yet to revise the report. After receiving the updated IEE from PMC, it shall be finalised. | Soft copy of Final DPR received, BoQ to be corrected in house for preparation of Bid Document.
|  |  |  | 17 | # Conservation and Restoration of Gulabi Kothi |  |  | 2016-05-20 | 2016-05-23 | 3.34 | 3.59 | 2016-06-25 |  |  |  | Do
|  |  |  | 18 | # Conservation and Adaptive reuse of the Gol Kothi & Civil Rest House - Renovation, Landscaping, external lighting and visitors facilities. |  |  | 2016-05-20 | 2016-05-23 | 3.52 | 4.91 | 2016-06-25 |  |  |  | Do
[5 empty] | Total Package cost | [5 empty] | 16.18
[5 empty] | TOTAL | 48.66 |  |  |  | 47.25 | 54.4
SHADED PROJECTS (10 NOs.) ARE ON PRIORITY
Status for Environment Monitoring Report (EMR): 1.Quarterly Environmental Monitoring Report (QEMR) for Tranche-1 for quarters: i) Jan- March'16 ii) Apr- June'16 is submitted to ADB. 2. Semi- annual Environmental Monitoring Report (SEMR) for Tranche-3 from Jan- June'16 is submitted to ADB. 3. QEMR for quarter ending July- Sept'16 is under preparation. 4. SEMR for the reporting period from July-Dec'16 is under preparation.